## RTM
Requirement ID | Requirement Description | Requirement Type | Priority | Module | Test Case ID | Test Execution Status | Defect ID | Requirement Status | Remarks
Req-SC1 | Page should load footer section without continuous element loading | Functional | High | Home Page Module | 201 | Not Started | D-201 | In Progress | Critical issue blocking footer access
Req-SC2 | Search should display message when showing alternative results due to no exact match | Functional | High | Search Module | 202 | Not Started | D-202 | In Progress | User feedback - improve clarity
Req-SC3 | All product categories should have their respective images displayed on Home Page | Functional | High | Category Module | 203 | Not Started | D-203 | In Progress | Missing Pet Supplies category
Req-SC4 | Become a Supplier page should have back button and consistent layout with main website | Functional | Medium | Navigation Module | 204 | Not Started | D-204 | In Progress | Layout inconsistency issue
Req-SC5 | Delete Account option should only be visible to logged-in users | Functional | Critical | Account Module | 205 | Not Started | D-205 | In Progress | Security concern - must fix

## Test Case
Project Name: |  |  | MEESHO WEBSITE
Module Name: |  |  | Home Page & Search Module
Created By: |  |  | Karthik B
Date of Creation: |  |  | 2026-03-08
Test Case Id | Requirement Id | Test Case Scenario | Test Case Description | Precondition | Test case steps Taken | Test Data | Expected Result | Actual Result | Status | Defect Id
201 | Req-SC1 | Verify footer loads without continuous page element loading | Validate that footer section is accessible and loads without blocking other page elements | User is on Home Page; Page has finished initial load | 1. Scroll down to bottom 2. Observe footer loading 3. Check element rendering |  | Footer visible without continuous loading spinners |  | Not Started
202 | Req-SC2 | Verify search result message for alternative results | When search query doesn't match, system should display message about alternative keyword | User on Home Page; Access to search bar | 1. Click search bar 2. Enter 'hello bag' 3. Press Enter 4. Observe results page | Search Query: hello bag | Display message like: Showing results for yellow bag |  | Not Started
203 | Req-SC3 | Verify all category images displayed on Home Page | All product categories including Pet Supplies should show respective images | User on Home Page; Page fully loaded; Scrolled to category section | 1. Navigate to Home Page 2. Scroll to categories section 3. Check Pet Supplies image 4. Verify other categories |  | Pet Supplies image visible; All categories show product images |  | Not Started
204 | Req-SC4 | Verify Become a Supplier page has back button and consistent layout | Page should have back button and maintain consistent header/footer with main website | User on Home Page; Can see header navigation | 1. Click Become a Supplier link 2. Check for back button 3. Verify header footer consistency 4. Click back button | Page URL: supplier section | Back button visible and functional; Header footer match main design |  | Not Started
205 | Req-SC5 | Verify Delete Account visible only to logged-in users | Delete Account option should not display to non-logged-in users | User not logged in; On account/profile page; Cookies cleared | 1. Without login, navigate to account settings 2. Search for Delete Account 3. Verify visibility 4. Login and recheck | Test User: Non-logged-in, Browser: Chrome Incognito | Delete Account NOT visible when logged out; Visible after login |  | Not Started

## Bugs
Bug ID | Detected Date | Updated Date | Req Id | Status | Severity | Priority | Title | Module | Version | Build | Is it reproducible | Reported by
D-201 | 2025-10-17 | 2025-10-17 | Req-SC1 | Open | High | High | Footer section not loading - continuous refresh | Home Page | v1.0 | 201 | Yes | Karthik B
D-202 | 2025-10-17 | 2025-10-17 | Req-SC2 | Open | Medium | Medium | Missing feedback message for alternative results | Search Module | v1.0 | 201 | Yes | Karthik B
D-203 | 2025-10-17 | 2025-10-17 | Req-SC3 | Open | High | High | Pet Supplies category image not displayed | Category Module | v1.0 | 201 | Yes | Karthik B
D-204 | 2025-10-18 | 2025-10-18 | Req-SC4 | Open | Medium | Medium | Back button missing and layout inconsistent | Navigation | v1.0 | 201 | Yes | Karthik B
D-205 | 2025-10-18 | 2025-10-18 | Req-SC5 | Open | Critical | Critical | Delete Account visible to non-logged-in users | Account Module | v1.0 | 201 | Yes | Karthik B

## Test Execution Report
Requirement ID | Module | Test Case ID | Executed By | Execution Date | Execution Status | Defect ID | Comments
Req-SC1 | Home Page Module | 201 | QA Team | 2025-10-18 | Failed | D-201 | Footer continuously loading
Req-SC2 | Search Module | 202 | QA Team | 2025-10-18 | Failed | D-202 | No user message displayed
Req-SC3 | Category Module | 203 | QA Team | 2025-10-18 | Failed | D-203 | Pet Supplies image missing
Req-SC4 | Navigation | 204 | QA Team | 2025-10-18 | Failed | D-204 | Back button and layout issues
Req-SC5 | Account Module | 205 | QA Team | 2025-10-18 | Failed | D-205 | Security issue critical

## Test Summary Report
Module | Total Test Cases | Executed | Not Executed | Passed | Failed | Priority
Home Page Module | 1 | 1 | 0 | 0 | 1 | High
Search Module | 1 | 1 | 0 | 0 | 1 | High
Category Module | 1 | 1 | 0 | 0 | 1 | High
Navigation | 1 | 1 | 0 | 0 | 1 | Medium
Account Module | 1 | 1 | 0 | 0 | 1 | Critical

## Test Case Review
Test Case ID | Review Date | REVIEWER | COMMENTS | TESTER COMMENTS
201 | 2025-10-18 | Senior QA Lead | Test steps clear, good coverage | Approved
202 | 2025-10-18 | Senior QA Lead | Verified with product team | Approved
203 | 2025-10-18 | Senior QA Lead | Testing on multiple resolutions | Approved
204 | 2025-10-18 | Senior QA Lead | Added CSS validation steps | Approved
205 | 2025-10-18 | Senior QA Lead | Critical security test | Escalated